## Sheet1
| October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | Febuary |  |  |  | March |  |  |  |  | April
Task | 6th | 13th | 20th | 27th | 3rd | 10th | 17th | 24th | 1st | 8th | 15th | 22nd | 29th | 5th | 12th | 19th | 26th | 2nd | 9th | 16th | 23rd | 2nd | 9th | 16th | 23rd | 30th | 6th | 13th | 20th | 27th
Background reading
Get wind tunnel footage
Software planning
Software Development
Data labelling
Separate skydivers from background
Approximate skydivers skeletons
Map skeleton positions to formations
Unforseen problems
Fit stick man model to skeleton
Develop point distribution model
Finalise code
Report writing
First draft
Second draft
Final report
Progress report
First draft
Final report
Note on O1: Exam period
Note on K2: 9th December Deadline: Progress Report
Note on M2: In france: 12th - 20th Dec
Note on AE2: 28th April Deadline: Final Report