## Sheet1
Potential Problem | Loss (1-5) | Probibility (1-5) | Risk | Plan
Unable to get suitable stock FS footage | 4 | 3 | 12 | Contact FS coaches to ask for stock footage. If this is not possible, record a training session in the wind tunnel with my 4-way FS team.
Source code lost due to home computer failure | 5 | 1 | 5 | All source code and project documentation is backed up on private github repository.
Severe Illness | 4 | 1 | 4 | Time is factored into the initial Gantt chart to account for unforseen problems such as illness.
Creating an active shape model is more difficult and time consuming than expected | 4 | 3 | 12 | More time can be contributed to the project, should this be the case.
Fitting a stick man model to a skeleton is more difficult and time consuming than expected | 4 | 3 | 12 | More time can be contributed to the project, should this be the case.
No project work is completed during the exam period, and the project falls behind sechedule | 3 | 4 | 12 | After the exam period, extra time can be contributed to the project.